## Sheet1
Task | Start Date | Days to Complete
Build Skeleton | 2017-09-19 | 3
Login Screen | 2017-09-20 | 1
Baby Menu | 2017-09-21 | 3
Color Screen Start | 2017-09-24 | 7
Settings Screen Start | 2017-09-28 | 7
Timer Screen Start | 2017-09-30 | 5
Registration Screen | 2017-10-06 | 5
UI Polish | 2017-10-08 | 2
Message Board | 2017-10-11 | 7
Server set up | 2017-10-17 | 7
Data Fetching implementation | 2017-10-23 | 5
Timer Screen Polish | 2017-10-26 | 2
Registration Screen Polish | 2017-10-31 | 5
Color Screen Finish | 2017-11-03 | 3
UI Polish | 2017-11-04 | 2
Debug & Testing | 2017-11-06 | 3
Final Touches | 2017-11-09 | 3
Google Play upload | 2017-11-14 | 1